## Sheet1
Stoughton PC - Gaulby Lane Play Area | Agility - Balance Trail | Strimmer damage is present on posts, allowing water to enter and timbers to soften. It can also remove the protective envelope around the timber. Prevent further damage and check timbers for decay throughout the year. | Strimmer damage is present on posts, allowing water to enter and timbers to soften. Prevent further damage and check timbers for decay throughout the year. | Prevent further damage. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Agility - Roller Balance Beam | The supporting components should be dismantled and inspected according to the manufacturer's instructions. This will need doing on a regular basis, as defined by the manufacturer. This can lead to a high risk if no action is taken. | Unit has limited movement. | Dismantle and inspect according to manufacturer's instructions. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Agility - Roller Balance Beam | There are natural splits / shakes in the timbers. |  | Monitor and sand back any splintered edges as required. | 6 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Agility - Wobble Board | Item is rusting in places. | Spring connectors. | Descale. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Basketball Post | Risk assessment. | Balls may leave the area and strike a user of the play equipment. | Read the notes for further action. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Basketball Post | Loose in ground. | Slightly loose in the ground socket and leaning forwards. | Read the notes for further action. | 6 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Carousel - Dizzy Discs x 2 | Item is not secure. | Both rubber tops. | Secure. | 5 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Carousel - Turnstile | Bearings require service. |  | Service the bearings. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Football Goal | Mole hills present. | Throughout. | Eliminate. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Football Goal | Loose in ground. |  | Repair. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Football Goal | Risk assessment. | Balls may leave the area and strike a user of the play equipment. | Read the notes for further action. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Item is damaged. | Unit has been taped off from users due to damage to unit. Replace and repair damaged sections. Remove attached ropes. | Read the notes for further action. | 12 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Timber is not in good condition. | Several timbers throughout unit. Replace affected parts. Replace access steps and platform timbers. | Replace. | 10 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | RoSPA is concerned by accidents on some types of overhead ladders and rings. However, there is a strong development value in these items. |  | The protective surface under all bars and rings must be kept in good condition. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Item edges are worn. | Tyres are worn exposing metal frames. Replace. | Read the notes for further action. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Finger entrapment. | Slide platform gaps. Bridge slats. | Eliminate the entrapment. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Algae growth giving slippery conditions. | Surface / the equipment are algae and moss covered, providing a slippery surface when wet. | Powerwashing is recommended. Care should be taken to ensure that the material can sustain high pressure washing. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Chain covers prevent a thorough inspection of all chain links. | All chain covers are damaged leaving sharp edges. Replace. | Remove chain covers to inspect according to manufacturer's instructions, and replace the covers when done. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Some chain wear. |  | Monitor for further deterioration and replace before 40% wear. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Senior | Fixtures loose or missing. | Slide tower roof is loose due to missing fixings. | Tighten/replace. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Toddler | Timber is not in good condition. | Several timbers throughout unit. Replace. | Replace. | 10 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Multiplay - Toddler | Finger entrapment. | Platform gaps. | Eliminate the entrapment. | 6 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Dog | The spring is rusty. These have been known to fail without warning, leading to a collapse of the unit. |  | Monitor. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Dog | Bolt(s) loose. | Rocker body bolts to connectors. | Tighten. | 8 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Dog | Protruding handles / foot rests. |  | No reasonably practicable action is identified. | 3 | Very Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Seesaw | Fixtures loose or missing. | Foundation plate is very loose. Secure. | Tighten/replace. | 10 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Seesaw | Cap missing. |  | Replace. | 5 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Seesaw | Protruding handles / foot rests. |  | No reasonably practicable action is identified. | 3 | Very Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Rocker - Seesaw - Gullwing | Fixtures loose or missing. | One seat bolt fixtures. Replace. Hand hold bolts. Tighten. | Tighten/replace. | 7 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Seating - Various | Projecting bolt thread. |  | Cut off and file down to remove sharp edges or use the correct length of bolt. | 6 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Seating - Various | Timber is splintered. |  | Repair. | 5 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Seating - Various | The equipment is dirty or algae covered. |  | Clean off. | 5 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Swing - Junior - 1 Bay 2 Seat | There is wear in the bushes. | One hanger bush. | Remove shackle bolt and check bush and shackle pin wear, replacing as necessary. | 9 | Medium | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Swing - Junior - 1 Bay 2 Seat | There is wear to the surfacing due to foot drag. |  | Although the seats are set at an acceptable height it is recommended that these are raised by 100 mm to help prevent wear. | 6 | Low | 2023-08-07
Stoughton PC - Gaulby Lane Play Area | Swing - Toddler - 1 Bay 2 Seat | There is wear to the surfacing due to foot drag. |  | Although the seats are set at an acceptable height it is recommended that these are raised by 100 mm to help prevent wear. | 6 | Low | 2023-08-07